## Weekly Summary
Weekly Work Summary - MDMPI.App (Mobile App API)
Week of Aug 24-28, 2026 ¦ Branch: prod/websocket-location ¦ Based on committed work only (commits 4a02564, e673fee)
Operational Highlights | Challenge / Issue / Risk | Action Plan
Added a startup safety guard that blocks the API from connecting to the production database in Development unless ALLOW_PRODUCTION_DB=true is explicitly set (commit 4a02564, Program.cs). | Local development configuration points at live production databases - a developer running the API locally could unknowingly read/write production data. | Keep the guard in place permanently; set ALLOW_PRODUCTION_DB=true only when intentional. Longer term, provision a separate dev/staging database so local runs never touch production.
Introduced a dev-only middleware that rewrites /api4/* routes to /api/* so local calls match the production route prefix, and moved HTTPS redirection to run only outside Development (commit 4a02564). | Production serves the app under the /api4 prefix while local runs use /api, causing mismatched client calls and confusing 404s during local testing. | Middleware is scoped to Development only; verify production reverse-proxy prefix handling remains unchanged on next deployment.
Added automated tests: Api4RouteCompatibilityTests for the new route rewrite and updated WebSocketEndpointIntegrationTests for the DB guard. Full suite passing (91/91) with a clean build. | New startup guard could break existing integration tests that boot the API in the Development environment. | Continue running dotnet build/test locally before declaring work done (no CI pipeline exists yet); consider adding a CI workflow as a future improvement.
Expanded Clean Architecture implementation: added/updated DTOs, entities, repository and service interfaces and implementations for Logistics (AirSea, PickUp), Collection, and image features, following RESTful conventions (commit e673fee, 163 files). | Large surface of new code across Api/Core/Data layers increases regression risk; ItemModel remains an intentional exception to the RequestID primary-key rule and must not be 'corrected'. | Added/updated PickUp controller test cases; architectural rules and the ItemModel exception are now documented so future changes follow the same conventions.
Built a knowledge graph of the codebase (1,848 nodes, 3,205 edges, 108 communities) mapping every controller to its action methods, plus GRAPH_REPORT.md summarizing the architecture (commit e673fee). | Codebase knowledge was tribal; onboarding and impact analysis required manual code-reading across five projects. | Use the graph (graphify-out/) for architecture and dependency questions; regenerate it with /graphify as the code evolves rather than committing stale versions.
Documented agent/developer guidance: added CLAUDE.md (build, run, secrets, WebSocket rules) and docs/CODEX-TO-CLAUDE-TRANSITION.md migration plan; documented the WebSocket API and PostgreSQL schema dump (commit e673fee). | appsettings.json is tracked in git and contains live credentials (DB passwords, API keys); remediation requires credential rotation. | Secrets remediation is tracked as Phase 1 in docs/CODEX-TO-CLAUDE-TRANSITION.md - rotate credentials and move secrets to environment variables/user-secrets, pending maintainer's go-ahead.